## Sheet1
Project Plan — Bright Coffee Shop Sales Analysis (2 Weeks)
Task | Start Date | Duration (days) | Task | Start Offset (days) | Duration (days)
Planning & Architecture (Miro data flow diagram) | 2026-07-30 | 1 | Planning & Architecture (Miro data flow diagram) | 0 | 1
Project Gantt Chart & scope finalisation | 2026-07-31 | 1 | Project Gantt Chart & scope finalisation | 1 | 1
Load raw CSV into Databricks | 2026-08-01 | 1 | Load raw CSV into Databricks | 2 | 1
Data cleaning: cast unit_price, fix nulls/dupes | 2026-08-02 | 1 | Data cleaning: cast unit_price, fix nulls/dupes | 3 | 1
Build transaction_time_bucket + total_amount | 2026-08-03 | 1 | Build transaction_time_bucket + total_amount | 4 | 1
SQL: revenue by product/store/time (Databricks) | 2026-08-04 | 1 | SQL: revenue by product/store/time (Databricks) | 7 | 1
Export processed data; build Excel pivot tables | 2026-08-05 | 1 | Export processed data; build Excel pivot tables | 8 | 1
Build dashboards & charts in Excel | 2026-08-06 | 1 | Build dashboards & charts in Excel | 9 | 1
Draft insights & recommendations, start PPT | 2026-08-07 | 1 | Draft insights & recommendations, start PPT | 10 | 1
Finalise PPT, QA all files, push to GitHub | 2026-08-08 | 1 | Finalise PPT, QA all files, push to GitHub | 11 | 1